## Summary
ACH DB Next Day Validation (C-247489): Team Tracker Summary
All figures calculate from the Task Tracker and Shared Work sheets.
Person | Role | Ownership | Task Hours | Shared Hours | Total Hours | Active Hours (excl. Cut) | Hours Done | % Done | # Tasks | # Done | # In Progress | # Blocked | # Must Open
P1 | Engine Lead | Comparison engine, check types, findings, 5 Core Validations | 20 | 5 | 25 | 20 | 0 | 0% | 12 | 0 | 0 | 0 | 9
P2 | Config & Governance Lead | Rules file, schema, hot reload, hash/diff, what-if, config editor | 20 | 5 | 25 | 20 | 0 | 0% | 12 | 0 | 0 | 0 | 7
P3 | Backend, Decision & Audit Lead | API, run store, approve/investigate, SoD, audit chain, export, revalidate | 20 | 5 | 25 | 20 | 0 | 0% | 12 | 0 | 0 | 0 | 8
P4 | Frontend / UX Lead | Reviewer workbench UI and all non-config screens | 20 | 5 | 25 | 20 | 0 | 0% | 12 | 0 | 0 | 0 | 7
P5 | Data, QA & Pitch Lead | Synthetic data, tests, docs, deck, demo script, submission | 19.5 | 5 | 24.5 | 19.5 | 0 | 0% | 12 | 0 | 0 | 0 | 11
TEAM |  |  | 99.5 | 25 | 124.5 | 99.5 | 0 | 0% | 60 | 0 | 0 | 0 | 42
Workload balance
Average total hours per person |  |  | 24.9
Max minus min total hours (gap) |  |  | 0.5
Balance status |  |  | Balanced
Tasks by tag
Tag | Meaning | # Tasks | Hours | # Done
M | Must have (acceptance criteria / FAQ) | 42 | 72.5 | 0
N | Nice to have | 14 | 22.5 | 0
S | Stretch | 4 | 4.5 | 0
Assumptions
Plan assumes ~24 hours with feature freeze at hour 19; hours are planning estimates, not measured.
Shared Hours (5.0) apply equally to each person. Person totals differ slightly because P5 is at 19.5 task hours; C12 (NL drafting) is an unbudgeted floater.
Hard gates: Hr 8 = 5/5 seeded scenarios pass in pytest; Hr 14 = live config change works end to end; Hr 19 = freeze.

## Task Tracker
ID | Owner | Owner Role | Task | Detail | Maps To | Tag | Est. Hours | Planned Window | Depends On | Status | % Complete | Hours Done | Hours Left | Notes / Blockers
E1 | P1 | Engine Lead | Data model | Typed classes: Request, ChangeRecord (TNAL), GPSRecord, EvidenceIndicator, Finding, Result, CoreValidation. Agree with P2/P3/P5. | FAQ 8 | M | 1.5 | Hr 2-4 | Contracts | Not Started | 0% | 0 | 1.5
E2 | P1 | Engine Lead | Engine entry point | run(request, tnal, gps, evidence, config) -> Result. No file, DB or network access. | AC1, FAQ 8 | M | 1 | Hr 3-4 | E1 | Not Started | 0% | 0 | 1
E3 | P1 | Engine Lead | Check types (6) | exact_match, allowed_values, required_present, numeric_tolerance, no_unrequested_change, evidence_required. Structured findings. | AC2, AC3 | M | 4 | Hr 3-6 | E1 | Not Started | 0% | 0 | 4
E4 | P1 | Engine Lead | Normalizers | trim, casefold, collapse_whitespace, date_iso, numeric; applied per field from config. | AC2 | N | 1.5 | Hr 8-10 | E3 | Not Started | 0% | 0 | 1.5
E5 | P1 | Engine Lead | Categorization and reasons | Map failures to MISMATCH/MISSING/UNAUTHORIZED/EVIDENCE; plain-language reason templates. | AC3, FAQ 6 | M | 1.5 | Hr 6-7 | E3 | Not Started | 0% | 0 | 1.5
E6 | P1 | Engine Lead | Overall aggregation | Any BLOCKING exception = EXCEPTION else PASS. Enum must not contain APPROVED. | AC1, AC5 | M | 0.5 | Hr 6-7 | E3 | Not Started | 0% | 0 | 0.5
E7 | P1 | Engine Lead | Five Core Validations | Map findings to the 5 control validations; status per validation. | Process flow Step 6 | M | 2.5 | Hr 8-11 | E5 | Not Started | 0% | 0 | 2.5
E8 | P1 | Engine Lead | GPS vs TNAL cross-check + request-approved check | Validation 5 (GPS matches ACH) and Validation 1 (request exists and approved). | Process flow | M | 1.5 | Hr 10-12 | E7 | Not Started | 0% | 0 | 1.5
E9 | P1 | Engine Lead | Severity levels | BLOCKING vs WARNING per rule; warnings shown but do not force EXCEPTION. | Stretch | S | 1.5 | Hr 14-16 | E6 | Not Started | 0% | 0 | 1.5
E10 | P1 | Engine Lead | Engine unit tests | One test per check type, normalization edges, blank vs missing, determinism, no-I/O-imports test. | AC2, FAQ 10 | M | 2.5 | Hr 6-8 | E3 | Not Started | 0% | 0 | 2.5
E11 | P1 | Engine Lead | Diff spans | Character-level diff spans for MISMATCH so UI can highlight. | UX wow | N | 1.5 | Hr 12-14 | E5 | Not Started | 0% | 0 | 1.5
E12 | P1 | Engine Lead | Engine docs | Docstrings + one page on adding a check type via config only. | Deliverable | M | 0.5 | Hr 16-17 | E3 | Not Started | 0% | 0 | 0.5
C1 | P2 | Config & Governance Lead | rules.yaml v1 | Rules for all seeded fields, mandatory fields, evidence reqs, unrequested_changes policy, version_label, templates. | AC4, FAQ 4 | M | 1.5 | Hr 2-4 | Contracts | Not Started | 0% | 0 | 1.5
C2 | P2 | Config & Governance Lead | Schema validation | Pydantic config models; reject unknown checks/missing fields/bad tolerances with friendly messages. | Demo safety | M | 2 | Hr 4-6 | C1 | Not Started | 0% | 0 | 2
C3 | P2 | Config & Governance Lead | Loader, re-read per run | No module-level cache; re-read on every /validate; keep last-good config if new one invalid. | AC4, FAQ 4/10 | M | 1.5 | Hr 6-8 | C2 | Not Started | 0% | 0 | 1.5
C4 | P2 | Config & Governance Lead | Config version + hash | version_label + SHA-256 (first 8 shown); stored in every run. | FAQ 7 | M | 1 | Hr 6-8 | C3 | Not Started | 0% | 0 | 1
C5 | P2 | Config & Governance Lead | Config diff | Structured diff active vs draft (added/removed/changed rules). | Governance | N | 1.5 | Hr 12-14 | C2 | Not Started | 0% | 0 | 1.5
C6 | P2 | Config & Governance Lead | Config endpoints | GET/PUT /config, POST /config/validate, POST /reset. Coordinate with P3. | AC4 | M | 1.5 | Hr 8-10 | C3, B1 | Not Started | 0% | 0 | 1.5
C7 | P2 | Config & Governance Lead | Config editor UI | YAML editor, inline errors, Save, Reset, one-click demo presets, version/hash badge. | AC4 live | M | 3.5 | Hr 10-14 | C6 | Not Started | 0% | 0 | 3.5
C8 | P2 | Config & Governance Lead | What-if engine | POST /whatif: run all 5 scenarios on active vs draft; before/after matrix with flips. | Dark horse | N | 2 | Hr 12-14 | C3, E2 | Not Started | 0% | 0 | 2
C9 | P2 | Config & Governance Lead | What-if matrix UI | Scenarios x (current, draft); red flip warnings; shown before Save. | Dark horse | N | 2 | Hr 14-16 | C8 | Not Started | 0% | 0 | 2
C10 | P2 | Config & Governance Lead | Config change log | Append-only: timestamp, actor, old->new hash, required reason, diff. Goes into audit pack. | Governance | N | 1.5 | Hr 16-18 | C6 | Not Started | 0% | 0 | 1.5
C11 | P2 | Config & Governance Lead | Config tests | Live reload, invalid YAML rejected, hash changes, what-if correct, stale config never used. | AC4 | M | 2 | Hr 16-19 | C8 | Not Started | 0% | 0 | 2
C12 | P2 | Config & Governance Lead | NL rule drafting (optional floater) | LLM proposes YAML diff; human must confirm; never auto-applies; labeled advisory. Only if everything else is green. Not in hour totals. | Stretch | S | 0 | Floater | All frozen | Not Started | 0% | 0 | 0
B1 | P3 | Backend, Decision & Audit Lead | Scaffolding | Repo layout, FastAPI app, Makefile (setup/test/run), CORS. | Submission | M | 1.5 | Hr 2-4 | Contracts | Not Started | 0% | 0 | 1.5
B2 | P3 | Backend, Decision & Audit Lead | Simulated source loaders | Loaders for ServiceNow/DMS, TNAL, GPS, evidence; every response has source=SIMULATED. | AC6 | M | 1.5 | Hr 3-5 | B1, D2 | Not Started | 0% | 0 | 1.5
B3 | P3 | Backend, Decision & Audit Lead | Scenario and validate endpoints | GET /scenarios (with expected outcome), POST /validate (fresh config, engine, create run). | AC1 | M | 1.5 | Hr 5-6 | B2, E2 | Not Started | 0% | 0 | 1.5
B4 | P3 | Backend, Decision & Audit Lead | Run store | SQLite/JSONL; run IDs (RUN-YYYYMMDD-NNNN); all FAQ 7 fields. | FAQ 7 | M | 2 | Hr 6-8 | B3 | Not Started | 0% | 0 | 2
B5 | P3 | Backend, Decision & Audit Lead | Decision endpoint | Approve/Investigate + notes; state machine VALIDATED -> APPROVED/INVESTIGATE; no auto-decision path. | AC5 | M | 1.5 | Hr 8-10 | B4 | Not Started | 0% | 0 | 1.5
B6 | P3 | Backend, Decision & Audit Lead | SoD enforcement | Maker from TNAL record; reject if checker_id == maker_id; log violation attempt; persona directory. | AC6, FAQ 3 | M | 2 | Hr 10-12 | B5 | Not Started | 0% | 0 | 2
B7 | P3 | Backend, Decision & Audit Lead | Run history API | GET /runs, filters, PASS/EXCEPTION counts, counts by rule. | Business story | N | 1 | Hr 12-13 | B4 | Not Started | 0% | 0 | 1
B8 | P3 | Backend, Decision & Audit Lead | Hash-chained audit log | prev_hash/record_hash on run, decision, config-change, SoD events; GET /audit/verify finds first broken link. | Audit-ready | N | 2.5 | Hr 16-18 | B4 | Not Started | 0% | 0 | 2.5
B9 | P3 | Backend, Decision & Audit Lead | Audit pack export | Per-run JSON + printable HTML/PDF: header, config hash, findings, decision, notes, chain proof; SIMULATED label. | FAQ 10 | N | 2 | Hr 17-19 | B8 | Not Started | 0% | 0 | 2
B10 | P3 | Backend, Decision & Audit Lead | Revalidate loop | After Investigate, load corrected TNAL and rerun; link via parent_run_id. | Process flow | S | 2 | Hr 19-21 | B5 | Not Started | 0% | 0 | 2
B11 | P3 | Backend, Decision & Audit Lead | API tests | No-auto-approve, SoD block, decision-before-validate rejected, metadata completeness, chain tamper, revalidate link. | AC5, AC6 | M | 2 | Hr 13-16 | B6 | Not Started | 0% | 0 | 2
B12 | P3 | Backend, Decision & Audit Lead | API docs | API reference + README run section. | Deliverable | M | 0.5 | Hr 19-20 | B9 | Not Started | 0% | 0 | 0.5
U1 | P4 | Frontend / UX Lead | Layout and design system | App shell, tokens, projector-sized type, persistent SIMULATED banner, persona switcher. | AC6 | M | 2 | Hr 2-4 | Contracts | Not Started | 0% | 0 | 2
U2 | P4 | Frontend / UX Lead | Scenario picker | 5 scenarios with title, category, expected badge, matches-expected indicator. | AC2 | M | 1.5 | Hr 4-6 | U1 | Not Started | 0% | 0 | 1.5
U3 | P4 | Frontend / UX Lead | Run metadata header | Run ID, request ID, TNAL/GPS IDs, config version+hash, timestamp, maker, checker. | FAQ 7 | M | 1 | Hr 6-7 | U2 | Not Started | 0% | 0 | 1
U4 | P4 | Frontend / UX Lead | Result banner and exception cards | PASS/EXCEPTION banner; card per finding with six FAQ-6 fields; color by category. | AC1, AC3 | M | 3 | Hr 6-8 | U2, B3 | Not Started | 0% | 0 | 3
U5 | P4 | Frontend / UX Lead | Expected vs Actual view | Side-by-side with character highlights; (blank) and 'not requested' states. | UX wow | N | 2 | Hr 12-14 | U4, E11 | Not Started | 0% | 0 | 2
U6 | P4 | Frontend / UX Lead | Five Core Validations panel | 5 rows with pass/fail status, clickable to filter findings. | Process flow | M | 1.5 | Hr 8-10 | E7 | Not Started | 0% | 0 | 1.5
U7 | P4 | Frontend / UX Lead | Decision panel | Approve/Investigate, notes, confirm step, SoD red block banner, decided lock, no-auto-approval microcopy. | AC5, AC6 | M | 2.5 | Hr 10-12 | B5, B6 | Not Started | 0% | 0 | 2.5
U8 | P4 | Frontend / UX Lead | Run history and analytics | History table (run, scenario, result, config hash, decision) + small counts by rule. | Business story | N | 1.5 | Hr 13-15 | B7 | Not Started | 0% | 0 | 1.5
U9 | P4 | Frontend / UX Lead | Audit pack view | Export button, printable view, Verify integrity button (chain OK/broken). | FAQ 10 | N | 1.5 | Hr 17-19 | B8, B9 | Not Started | 0% | 0 | 1.5
U10 | P4 | Frontend / UX Lead | Revalidate UI | Revalidate button after Investigate; parent/child run display. | Process flow | S | 1 | Hr 19-20 | B10 | Not Started | 0% | 0 | 1
U11 | P4 | Frontend / UX Lead | Demo-readiness features | Reset button, loading/error states, keys 1-5 for scenarios, empty states, demo mode. | Demo safety | M | 1.5 | Hr 15-17 | U7 | Not Started | 0% | 0 | 1.5
U12 | P4 | Frontend / UX Lead | Final polish | Spacing, contrast, projector resolution check, copy review. | Presentation | N | 1 | Hr 21-23 | Freeze | Not Started | 0% | 0 | 1
D1 | P5 | Data, QA & Pitch Lead | Traceability matrix | AC1-6, FAQ 1-12, 12-item checklist, 5 Core Validations mapped to file, test, demo moment. Maintained throughout. | All | M | 1.5 | Hr 2-24 | Contracts | Not Started | 0% | 0 | 1.5
D2 | P5 | Data, QA & Pitch Lead | Seeded synthetic data | 5 requests, 5 TNAL, 5 GPS, evidence indicators, expected_outcomes.json, personas. Fake IDs only. | AC2, AC6 | M | 2.5 | Hr 2-5 | Contracts | Not Started | 0% | 0 | 2.5
D3 | P5 | Data, QA & Pitch Lead | Edge-case data | Normalization case, GPS!=ACH, request-not-approved, multi-exception, severity warning. Separate from the 5. | Robustness | N | 1 | Hr 12-14 | D2 | Not Started | 0% | 0 | 1
D4 | P5 | Data, QA & Pitch Lead | Demo edit presets | Design live-edit story (e.g. make authorization form optional so Scenario 5 flips); hand presets to P2, click path to P4. | AC4 | M | 1 | Hr 6-8 | C1 | Not Started | 0% | 0 | 1
D5 | P5 | Data, QA & Pitch Lead | Seeded scenario test suite | Parametrized pytest on expected_outcomes.json: 5 outcomes, six explainability fields, metadata completeness. | AC2, AC3 | M | 2 | Hr 6-8 | E2, D2 | Not Started | 0% | 0 | 2
D6 | P5 | Data, QA & Pitch Lead | End-to-end smoke test | Playwright script of full click path: scenarios, SoD block, config flip, decision. Run before each rehearsal. | Demo safety | M | 1.5 | Hr 13-16 | U7, C7 | Not Started | 0% | 0 | 1.5
D7 | P5 | Data, QA & Pitch Lead | Guardrail audit | Script scanning data for PII/account numbers + checklist (SIMULATED labels, SoD, no auto-approval); AC6 evidence sheet. | AC6 | M | 1 | Hr 8-10 | D2 | Not Started | 0% | 0 | 1
D8 | P5 | Data, QA & Pitch Lead | Architecture summary | 1-2 page doc: engine/config/UI split, data flow, SIMULATED sources, diagram, config-only extension, assumptions. | Deliverable | M | 2 | Hr 8-17 | E12 | Not Started | 0% | 0 | 2
D9 | P5 | Data, QA & Pitch Lead | Decks (5/3/10 min) | 5-min primary + 3 and 10-min variants; AC1-AC6 proof slide, architecture slide, honest business-value slide. | Deliverable | M | 3 | Hr 12-20 | D1 | Not Started | 0% | 0 | 3
D10 | P5 | Data, QA & Pitch Lead | Demo script and walkthrough | Timed click-by-click per FAQ 9, recovery lines, written walkthrough doc. | Deliverable | M | 1.5 | Hr 16-19 | D4 | Not Started | 0% | 0 | 1.5
D11 | P5 | Data, QA & Pitch Lead | Rehearsal lead | 5 timed rehearsals, log timings, rehearse failure recovery. | Demo | M | 1 | Hr 19-23 | D10 | Not Started | 0% | 0 | 1
D12 | P5 | Data, QA & Pitch Lead | Submission package | Backup video, README final pass, 12-item checklist with evidence links, repo cleanup, upload. | Submission | M | 1.5 | Hr 21-24 | D11 | Not Started | 0% | 0 | 1.5
Legend
Tag: M = Must (AC/FAQ), N = Nice-to-have, S = Stretch. Blue text = cells to edit (Status, % Complete, Notes, Hours).
Hours Done = Est. Hours x % Complete. Set Status to 'Cut' for dropped tasks; they are excluded from the Summary 'Active Hours'.
C12 is an unbudgeted floater (0 hours); put actual hours in H if you pick it up. Estimates are planning assumptions, not measured.

## Shared Work
Shared team activities (apply to all 5 people)
Hours per person per activity. Counted once per person in the Summary.
ID | Activity | When | Hours / Person | Status | Notes
S1 | Kickoff, contract lock, spec reread | Hr 0-2 | 1.5 | Not Started
S2 | Integration checkpoints (3 x 20 min: hr 8, 14, 18) | Hr 8/14/18 | 1 | Not Started
S3 | Feature freeze and regression pass | Hr 19-20 | 0.5 | Not Started
S4 | Bug bash (try to break SoD, bad YAML, double-decision) | Hr 21 | 1 | Not Started
S5 | Rehearsals (5 x 12 min) | Hr 19-23 | 1 | Not Started
TOTAL |  |  | 5

## AC Traceability
AC | Requirement | Proving Tasks | Primary Owner | Supporting | Evidence / Demo Moment | Verified? (Y/N) | Evidence Link
AC1 | End-to-end PASS/EXCEPTION in checker summary | E2, E6, B3, U4 | P1 | P3, P4 | Seeded suite + UI banner | N
AC2 | Five seeded scenarios hit expected outcomes | D2, D5, E3 | P5 | P1 | pytest parametrized suite | N
AC3 | Explainable exceptions (field, expected, actual, rule, reason) | E5, U4, D5 | P1 | P4, P5 | Exception card + test of six fields | N
AC4 | Config-driven rule change, no code change | C1-C4, C7, C11 | P2 | P5 (D4) | Live flip + live-reload test | N
AC5 | Human approval; system never approves | B5, U7, B11 | P3 | P4 | No-auto-approve test + decision panel | N
AC6 | Guardrails: synthetic data, SoD, SIMULATED labels | B6, B2, U1, D7 | P3 | P4, P5 | SoD block demo + guardrail audit sheet | N
ACs verified |  | 0 of 6

## FAQ11 Checklist
# | Checklist Item (FAQ 11) | Owner | Done? (Y/N) | Evidence Link
1 | Synthetic maintenance requests created | P5 | N
2 | Synthetic TNAL/GPS reports created | P5 | N
3 | External rules configuration defined | P2 | N
4 | Comparison engine implemented | P1 | N
5 | All 5 seeded scenarios functional | P1 + P5 | N
6 | Reviewer summary UI built | P4 | N
7 | Discrepancy details and plain-language reasons surfaced | P1 + P4 | N
8 | Live rule modification verified without restart | P2 | N
9 | Reviewer decision capture (Approve / Investigate) | P3 + P4 | N
10 | Run metadata header displayed | P3 + P4 | N
11 | Segregation of Duties enforced | P3 | N
12 | 5-minute presentation rehearsed | P5 (all) | N
| Items complete | 0 of 12

## Gates & Cut Order
Hard gates
Gate | Hour | Pass Condition | Met? (Y/N)
G1 | 8 | 5/5 seeded scenarios pass in pytest. No UI polish before this. | N
G2 | 14 | Live config change works end to end (edit, rerun, outcome flips, hash changes). | N
G3 | 19 | FEATURE FREEZE. Anything unfinished is cut. | N
Cut order if time runs short (cut top-down)
Order | Cut Item | Task IDs
1 | C12 natural-language drafting | C12
2 | Revalidate loop (backend + UI) | B10, U10
3 | Severity levels | E9
4 | Audit export / UI (keep JSON dump) | B9, U9
5 | Hash-chained audit log | B8
6 | Run analytics | U8, B7
7 | Config change log | C10
8 | Character-level diff (fall back to plain highlight) | E11, U5
Never cut: E1-E3, E5-E8, E10, C1-C4, C6, C7, C11, B1-B6, B11, U1-U4, U6, U7, U11, and all D tasks except D3.

## Contracts
Shared contracts (lock at hours 0-2, all 5 together)
Contract | Definition | Agreed by all? (Y/N)
Finding object | finding_id, field, category (MISMATCH¦MISSING¦UNAUTHORIZED¦EVIDENCE), expected, actual, rule_id, rule_text, result (PASS¦EXCEPTION), severity (BLOCKING¦WARNING), reason, core_validation | N
Run record | run_id, request_id, tnal_report_id, gps_report_id, config_version_label, config_hash, timestamp, overall_result, findings[], core_validations[1..5], decision, decision_by, decision_notes, decision_timestamp, parent_run_id, prev_hash, record_hash | N
Endpoints | GET /scenarios, POST /validate, GET/PUT /config, POST /config/validate, POST /whatif, POST /decision, GET /runs, GET /runs/{id}, POST /runs/{id}/revalidate, GET /audit/verify, GET /export/{run_id}, POST /reset | N
Personas (fictional) | Maker: proc_jlee. Checkers: rev_mkhan, rev_apatel. Control owner: own_sbrown. | N
Result enum rule | Result states must never include APPROVED; only a human decision can approve. | N
Data rule | Synthetic only. Fake IDs (ACH-REQ-0001, ACME TEST CO). No account numbers. Label every integration SIMULATED. | N

## Timeline
Timeline by person (planned task windows)
Hours | P1 Engine | P2 Config | P3 Backend | P4 Frontend | P5 Data/QA/Pitch
0-2 | Contracts (all) | Contracts (all) | Contracts (all) | Contracts (all) | Contracts (all)
2-6 | E1-E3 | C1, C2 | B1-B3 | U1, U2 | D2, D1
6-8 | E5, E6, E10 | C3, C4 | B4 | U3, U4 | D5 (5/5 green gate), D4
8-12 | E7, E8, E4 | C6, C7 | B5, B6 | U6, U7 | D7, D8 draft
12-16 | E11, E9 | C5, C8, C9 | B7, B11 | U5, U8 | D3, D6, D9 skeleton
16-19 | E12 | C10, C11 | B8, B9 | U9, U11 | D10, D9 v2
19 | FEATURE FREEZE | FEATURE FREEZE | FEATURE FREEZE | FEATURE FREEZE | FEATURE FREEZE
19-21 | Bug fixes | Bug fixes | B10 (S) | U10 (S), U12 | D11, rehearsals
21-24 | Regression | Regression | Regression | Polish | D12, video, submit
Note: P4 windows use mock data until P3 endpoints land (hr 5-6); P1 diff spans (E11) are needed by P4 U5.